## #1 Application Details (hidden)
Application Details
1 | Applicant Organisation Name
2 | Applicant Organisation ABN
3 | Is the organisation registered for GST? Choose from dropdown list.
4 | Applicant Organisation Site Address
5 | Applicant Organisation Postal Address
6 | Primary Contact Person Name
7 | Primary Contact Person Email
8 | Primary Contact Person Phone
9a | Are you applying on behalf of another organisation (collaborative project)? Choose from dropdown list.
9b | If you answered yes to 9a, list the partner organisation name/s that will be involved in the project. If you answered no to 9a, skip to 10.
9c | If you answered yes to 9a, provide an overview of how the project partner/s will work with you to complete the project.
9d | If you answered yes to 9a, outline the roles and responsibilities the project partner/s will undertake, and the resources they will contribute.
10 | Names of all Directors and/or Board Members
11 | Total Grant Amount Request (exc GST) (Ensure this is the same as what you enter on your Budget (Tab 4))
12 | Proposed Project Start Date
13 | Proposed Project End Date
14 | Project Site Address
15 | Project Title
16 | Project Description (max 2000 characters)
17 | List the risks for the project and how these will be managed (max 2000 characters)
INSTRUCTIONS
Complete all 4 tabs (at the bottom of the page).
Enter your answers in the green boxes.

## Workplan
Workplan | [5 empty] | Workplan Reports
Objective/s (what the project will achieve) (choose from dropdown list) | Outcome/s (changes that will occur as a result of the project) (choose from dropdown list) | Indicator/s (how progress and success will be measured) | Life of Project Target/s (number) | Data Collection Method/s (how data will be collected) | Key Actions Planned For Each Reporting Period: A: 1 Jan 2026 - 30 Apr 2026 (4 months) B: 1 May 2026 - 31 Oct 2026 (6 months) C: 1 Nov 2026 - 30 Apr 2027 (6 months) | Progress Report 1 |  |  | Progress Report 2 |  |  | Progress Report 3 |  |  | Final Report
[6 empty] | 01/04/2025 to 31/10/2025 |  |  | 01/11/2025 to 30/04/2026 |  |  | 01/05/2026 to 31/10/2026 |  |  | 01/11/2026 to 30/04/2027 100% completion of project targets
[6 empty] | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary
1 | 1a
1b
1c
1d
2 | 2a
2b
2c
2d
Describe to what extent your project will achieve the applicable Objective/s and Outcome/s listed above (max 2000 characters)
INSTRUCTIONS
Complete the Workplan and Budget tabs.
Enter your answers in the green boxes.
Column B (dropdown options)
Choose which (or both) objective your project will achieve or "Not applicable". At least one objective must be chosen.
Column D (dropdown options)
For each Objective that you have chosen, choose all Outcomes that are applicable to your project or "Not applicable". At least one outcome must be chosen.
Column E
For each Outcome that you have chosen, nominate quantitative Indicators (things you can measure) that you will use to monitor the performance of your project. Examples include:
- Number of pollination-reliant businesses that have applied skills and knowledge gained through a CBIF grant project.
- Number of beekeepers that have applied skills and knowledge gained through a CBIF grant project.
- Number of targeted and purposeful education/engagement events delivered through a CBIF grant project.
- Number of attendees/participants in education/engagement events delivered through a CBIF grant project.
- Number of partnership-focused initiatives successfully delivered through a CBIF grant project.
- Number of new or improved management techniques developed as a result of a CBIF grant project.
- Number of new or improved monitoring techniques developed as a result of a CBIF grant project.
- Number of new or improved treatment techniques developed as a result of a CBIF grant project.
- Number of hives surveyed as a result of a CBIF grant project.
Column F
For each Indicator that you have chosen, nominate a Target (number) that your project will achieve over its entire life.
Column G
For each Indicator that you have chosen, describe how you will collect that data. Examples include:
- Participant survey results
- Monitoring results
- Attendance records
- Method/technique/tool launched for industry use
- Bee123 submissions
- Number of downloads
- Number of website hits
Column H
For each Outcome that you have chosen, describe the key actions you will undertake. Break these down into what actions you will take during each reporting period (specified) for the life of your project.
Row 41
Enter your answer in the green box.
Click here for Excel help

## #3 Expertise Summary (hidden)
Expertise Summary
Describe the expertise and capability you will utilise to deliver the project (max 2000 characters)
INSTRUCTIONS
Complete all 4 tabs (at the bottom of the page).
Enter your answer in the green box.
The Expertise Summary may include information regarding:
- key personnel, their role in this project, and their experience/qualifications
- examples of other relevant project experience and results
- proposed actions that will ensure the project will be delivered

## Budget
Budget |  |  |  | Reporting on Budget
|  |  |  | Progress Report 1 |  |  | Progress Report 2 |  |  | Progress Report 3 |  |  | Final Report
|  |  |  | 01/04/2025 to 31/10/2025 |  |  | 01/11/2025 to 30/04/2026 |  |  | 01/05/2026 to 31/10/2026 |  |  | 01/11/2026 to 30/04/2027 100% completion of project targets
Reporting Period (choose from dropdown list) | Budget Items (direct project related items) (choose from dropdown list) | Amount (exc GST) |  | Actual spend to date | Over or under planned spending? | Comments | Spend to date | Over or under planned spending? | Comments | Spend to date | Over or under planned spending? | Comments | Spend to date | Over or under planned spending? | Comments
Total Grant Amount Request (exc GST):
0
INSTRUCTIONS
For each reporting period (column A), list all the budget items (column B) and the amounts (column C) you will spend.
Enter your answers in the green boxes. Use as many lines as required.
Click here for Excel help

## Example Workplan 1
Workplan | [7 empty] | Workplan Reports
Objective/s (what the project will achieve) (choose from dropdown list) |  | Outcome/s (changes that will occur as a result of the project) (choose from dropdown list) |  | Indicator/s (how progress and success will be measured) | Life of Project Target/s (number) | Data Collection Method/s (how data will be collected) | Key Actions Planned For Each Reporting Period: A: 1 Jan 2026 - 30 Apr 2026 (4 months) B: 1 May 2026 - 31 Oct 2026 (6 months) C: 1 Nov 2026 - 30 Apr 2027 (6 months) | Progress Report 1 |  |  | Progress Report 2 |  |  | Progress Report 3 |  |  | Final Report
[8 empty] | 01/04/2025 to 31/10/2025 |  |  | 01/11/2025 to 30/04/2026 |  |  | 01/05/2026 to 31/10/2026 |  |  | 01/11/2026 to 30/04/2027 100% completion of project targets
[8 empty] | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary
1 | Not applicable | 1a
1b
1c
1d
2 | Objective 2 Innovative Tools: The development of innovative varroa mite management or monitoring tools. | 2a | Not applicable
|  | 2b | Outcome 2b. Queensland beekeepers adopt new or improved varroa mite management or monitoring techniques. | Number of new monitoring techniques developed and trialled as a result of a CBIF grant project. | 1 | Monitoring design trial undertaken and results evaluated and distributed. Monitoring technique design complete, peer reviewed and made freely available. | A: 1 Jan 2026 - 30 Apr 2026 (4 months) - Finalise new monitoring technique design, methodology, and equipment. - Undertake cost benefit analysis of new monitoring technique. - Seek peer and industry review of new monitoring technique. B: 1 May 2026 - 31 Oct 2026 (6 months) - Design monitoring trials. - Recruit and engage with trial participants. C: 1 Nov 2026 - 30 Apr 2027 (6 months) - Implement monitoring trials. - Record trial results. - Evaluate trial results. - Seek peer and industry review of trial results. - Distribute trial results publicly.
|  | 2c | Not applicable
|  | 2d | Outcome 2d. Varroa mite populations are slow to establish in new areas. | Number of hives surveyed as a result of a CBIF grant project. | 2000 | Monitoring trial participant records. | A: 1 Jan 2026 - 30 Apr 2026 (4 months) Nil B: 1 May 2026 - 31 Oct 2026 (6 months) Nil C: 1 Nov 2026 - 30 Apr 2027 (6 months) - Implement monitoring trials. - Record trial results. - Evaluate trial results.
Describe to what extent your project will achieve the applicable Objective/s and Outcome/s listed above (max 2000 characters) |  |  |  | Add your response here.
INSTRUCTIONS
Complete the Workplan and Budget tabs.
Enter your answers in the green boxes.
Column B (dropdown options)
Choose which (or both) objective your project will achieve or "Not applicable". At least one objective must be chosen.
Column D (dropdown options)
For each Objective that you have chosen, choose all Outcomes that are applicable to your project or "Not applicable". At least one outcome must be chosen.
Column E
For each Outcome that you have chosen, nominate quantitative Indicators (things you can measure) that you will use to monitor the performance of your project. Examples include:
- Number of pollination-reliant businesses that have applied skills and knowledge gained through a CBIF grant project.
- Number of beekeepers that have applied skills and knowledge gained through a CBIF grant project.
- Number of targeted and purposeful education/engagement events delivered through a CBIF grant project.
- Number of attendees/participants in education/engagement events delivered through a CBIF grant project.
- Number of partnership-focused initiatives successfully delivered through a CBIF grant project.
- Number of new or improved management techniques developed as a result of a CBIF grant project.
- Number of new or improved monitoring techniques developed as a result of a CBIF grant project.
- Number of new or improved treatment techniques developed as a result of a CBIF grant project.
- Number of hives surveyed as a result of a CBIF grant project.
Column F
For each Indicator that you have chosen, nominate a Target (number) that your project will achieve over its entire life.
Column G
For each Indicator that you have chosen, describe how you will collect that data. Examples include:
- Participant survey results
- Monitoring results
- Attendance records
- Method/technique/tool launched for industry use
- Bee123 submissions
- Number of downloads
- Number of website hits
Column H
For each Outcome that you have chosen, describe the key actions you will undertake. Break these down into what actions you will take during each reporting period (specified) for the life of your project.
Row 41
Enter your answer in the green box.
Click here for Excel help
Example Project - Develop a new varroa mite monitoring technique

## Example Workplan 2
Workplan | [7 empty] | Workplan Reports
Objective/s (what the project will achieve) (choose from dropdown list) |  | Outcome/s (changes that will occur as a result of the project) (choose from dropdown list) |  | Indicator/s (how progress and success will be measured) | Life of Project Target/s (number) | Data Collection Method/s (how data will be collected) | Key Actions Planned For Each Reporting Period: A: 1 Jan 2026 - 30 Apr 2026 (4 months) B: 1 May 2026 - 31 Oct 2026 (6 months) C: 1 Nov 2026 - 30 Apr 2027 (6 months) | Progress Report 1 |  |  | Progress Report 2 |  |  | Progress Report 3 |  |  | Final Report
[8 empty] | 01/04/2025 to 31/10/2025 |  |  | 01/11/2025 to 30/04/2026 |  |  | 01/05/2026 to 31/10/2026 |  |  | 01/11/2026 to 30/04/2027 100% completion of project targets
[8 empty] | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary | % Complete | Status | Commentary
1 | Objective 1 Innovative Engagement: The delivery of innovative community engagement regarding varroa mite. | 1a | Outcome 1a. Pollination-reliant industries in Queensland increase their knowledge of varroa mite and develop an awareness of the need to pay beekeepers for pollination services. | Number of pollination-reliant businesses that have applied skills and knowledge gained through a CBIF grant project. | 50 | Attendance survey results. | A: 1 Jan 2026 - 30 Apr 2026 (4 months) - Design and deliver a communications and engagement strategy to target pollination-reliant industries. B: 1 May 2026 - 31 Oct 2026 (6 months) - Plan event (venue, speakers, demonstrations, logistics, catering, materials). - Undertake event. C: 1 Nov 2026 - 30 Apr 2027 (6 months) - Evaluate outcomes of event.
|  | 1b | Not applicable
|  | 1c | Outcome 1c. Queensland beekeepers increase their knowledge and skills to incorporate varroa mite management into their business-as-usual activities. | Number of targeted and purposeful education/engagement events delivered through a CBIF grant project. | 1 | Event completion. | A: 1 Jan 2026 - 30 Apr 2026 (4 months) - Design and deliver a communications and engagement strategy to target pollination-reliant industries. - Design and deliver a communications and engagement strategy to target commercial and recreational beekeepers. B: 1 May 2026 - 31 Oct 2026 (6 months) - Plan event (venue, speakers, demonstrations, logistics, catering, materials). - Undertake event. C: 1 Nov 2026 - 30 Apr 2027 (6 months) - Evaluate outcomes of event.
|  |  |  | Number of attendees/participants in education/engagement events delivered through a CBIF grant project. | 100 | Attendance survey results. | A: 1 Jan 2026 - 30 Apr 2026 (4 months) - Design and deliver a communications and engagement strategy to target commercial and recreational beekeepers. B: 1 May 2026 - 31 Oct 2026 (6 months) - Plan event (venue, speakers, demonstrations, logistics, catering, materials). - Undertake event. C: 1 Nov 2026 - 30 Apr 2027 (6 months) - Evaluate outcomes of event.
|  | 1d | Not applicable
2 | Not applicable | 2a
2b
2c
2d
Describe to what extent your project will achieve the applicable Objective/s and Outcome/s listed above (max 2000 characters) |  |  |  | Add your response here.
INSTRUCTIONS
Complete the Workplan and Budget tabs.
Enter your answers in the green boxes.
Column B (dropdown options)
Choose which (or both) objective your project will achieve or "Not applicable". At least one objective must be chosen.
Column D (dropdown options)
For each Objective that you have chosen, choose all Outcomes that are applicable to your project or "Not applicable". At least one outcome must be chosen.
Column E
For each Outcome that you have chosen, nominate quantitative Indicators (things you can measure) that you will use to monitor the performance of your project. Examples include:
- Number of pollination-reliant businesses that have applied skills and knowledge gained through a CBIF grant project.
- Number of beekeepers that have applied skills and knowledge gained through a CBIF grant project.
- Number of targeted and purposeful education/engagement events delivered through a CBIF grant project.
- Number of attendees/participants in education/engagement events delivered through a CBIF grant project.
- Number of partnership-focused initiatives successfully delivered through a CBIF grant project.
- Number of new or improved management techniques developed as a result of a CBIF grant project.
- Number of new or improved monitoring techniques developed as a result of a CBIF grant project.
- Number of new or improved treatment techniques developed as a result of a CBIF grant project.
- Number of hives surveyed as a result of a CBIF grant project.
Column F
For each Indicator that you have chosen, nominate a Target (number) that your project will achieve over its entire life.
Column G
For each Indicator that you have chosen, describe how you will collect that data. Examples include:
- Participant survey results
- Monitoring results
- Attendance records
- Method/technique/tool launched for industry use
- Bee123 submissions
- Number of downloads
- Number of website hits
Column H
For each Outcome that you have chosen, describe the key actions you will undertake. Break these down into what actions you will take during each reporting period (specified) for the life of your project.
Row 41
Enter your answer in the green box.
Click here for Excel help
Example Project - Facilitate a varroa mite awareness field day

## Dropdowns (hidden)
Objectives
Objective 1 Innovative Engagement: The delivery of innovative community engagement regarding varroa mite. | Objective 1 Innovative Engagement: The development of innovative community engagement regarding Varroa mite.
Not applicable | Objective 2 Innovative Tools: The development of innovative Varroa mite management and monitoring tools.
Objective 2 Innovative Tools: The development of innovative varroa mite management or monitoring tools. | Both objectives
Not applicable
Status
Not yet started
On track
Minor delay
Major delay
Delivered
Outcomes
Outcome 1a. Pollination-reliant industries in Queensland increase their knowledge of varroa mite and develop an awareness of the need to pay beekeepers for pollination services. | Outcome 1a. Pollination-reliant industries in Queensland increase their knowledge of Varroa mite and develop an awareness of the need to pay beekeepers for pollination services.
Not applicable | Outcome 1b. Industries not targeted in conventional extension services increase their knowledge of Varroa mite.
Outcome 1b. Industries not targeted in conventional extension services increase their knowledge of varroa mite. | Outcome 1c. Queensland beekeepers increase their knowledge and skills to incorporate Varroa mite management into their business-as-usual activities.
Not applicable | Outcome 1d. Partnerships are formed to create mutually beneficial outcomes for monitoring or management of Varroa mite.
Outcome 1c. Queensland beekeepers increase their knowledge and skills to incorporate varroa mite management into their business-as-usual activities. | Outcome 2a. Queensland beekeepers access new or improved data-driven decision-making tools to choose appropriate Varroa mite management or monitoring techniques.
Not applicable | Outcome 2b. Queensland beekeepers adopt new or improved Varroa mite management or monitoring techniques.
Outcome 1d. Partnerships are formed to create mutually beneficial outcomes for monitoring or management of varroa mite. | Outcome 2c. The spread of Varroa mite across Queensland is limited to natural spread as much as possible.
Not applicable | Outcome 2d. Varroa mite populations are slow to establish in new areas.
Outcome 2a. Queensland beekeepers access new or improved data-driven decision-making tools to choose appropriate varroa mite management or monitoring techniques.
Not applicable
Outcome 2b. Queensland beekeepers adopt new or improved varroa mite management or monitoring techniques.
Not applicable
Outcome 2c. The spread of varroa mite across Queensland is limited to natural spread as much as possible.
Not applicable
Outcome 2d. Varroa mite populations are slow to establish in new areas.
Not applicable
Indicators
Number of pollination-reliant businesses that have applied skills and knowledge gained through a CBIF grant project.
Number of beekeepers that have applied skills and knowledge gained through a CBIF grant project.
Number of targeted and purposeful education/engagement events delivered through a CBIF grant project.
Number of attendees/participants in education/engagement events delivered through a CBIF grant project.
Number of partnership-focused initiatives successfully delivered through a CBIF grant project.
Number of new or improved management techniques developed as a result of a CBIF grant project.
Number of new or improved monitoring techniques developed as a result of a CBIF grant project.
Number of new or improved treatment techniques developed as a result of a CBIF grant project.
Number of hives surveyed as a result of a CBIF grant project.
exc GST
inc GST
Yes
No
FY25/26
FY26/27
1 Jan 2026 - 30 Apr 2026
1 May 2026 - 31 Oct 2026
1 Nov 2026 - 30 Apr 2027
CBIF grant funds
In-kind contribution
Applicant financial contribution
Other external funding source
Over
Under
General operating costs
Business as usual costs
Staff wages or salaries for employees’ time
Travel costs
Contractor or consultant fees
Catering and event costs
Material and equipment